## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Studied Assesment and User Stories | 0.5 | 2025-12-06 | I went through assessment, cerefully studying requirements, user stories, style guide, and desktop and mobile workflow to build an idea on how final product should look like.
Initialized repository | 0.5 | 2025-12-06 | I initialized project and uploaded it to github. After I moved all media files to assets folder and structured it with dedicated folders - /images to placeholder images and /icons for icons images in this way I can structure all project media files. After I defined necessary css variables and font families to adhear to DTT Style Guide.
User Story 1 ¦ Developed page layout and setted up routing | 1 | 2025-12-06 | I decided to use vue router to manage different pages in application as this library allows to use have reusable layout components for different pages, with that I created DefaultLayout and FormLayout component, those components share same header compoent, and are applyed to all pages on application according to its view. Also vue router allows to create easy styling for active links on header which I used to give appropriate styling to links in header.
Developed State Manager | 1 | 2025-12-06 | Made service for communication with API, created state store with pinia
User Story 2 ¦ Developed home page | 2 | 2025-12-06 | Created /ui subfolder in /components to store BaseIcon, PrimaryButton, IconButton, SearchInput, ToggleTabs. Then developed House card component. Then I develed HomePage.
User Story 2 ¦ Developed search for home page | 1 | 2025-12-06
2025-12-06
Total amount of hours | 5.5